## Sheet1
St. Charles Place
Interior Remodel Progress Report
Data as of: |  | 2018-07-31 | [5 empty] | Total Units Budgeted | Total Units Completed | Yet to do | Currently In Process | Budgeted Rehab Cost | Average Actual Rehab Cost | Occupied Completions | Average Rent Increase |  | Average ROI |  | UW Remodel Rent Increase | Yardi Protected Value
[6 empty] | 1 BR Full | Including appliances | 90 | 15 | 75 | 3 | 3523 | 3461.9015 | 15 | 75 |  | 28.96% |  |  | 0
[6 empty] | 1 BR Partial | Including appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  | 0
[6 empty] | 2 BR Full | Including appliances | 45 | 17 | 28 | 3 | 5054 | 4820.3077 | 15 | 93.6667 |  | 24.79% |  |  | 0
[6 empty] | 2 BR Partial | Including appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  | 95
[6 empty] | 3 BR Full | Including appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  | 0
[6 empty] | 3 BR Partial | Including appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  | 0
[6 empty] | Appliances | Kitchen appliances only | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  | 0
[6 empty] | W/D | Washer/dryer only | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  | 0
[8 empty] | 135 | 32 | 103 | 6 | 544500 | 4183.5548 | 30 | 84.3333 |  | 26.96% |  | 0 | 0
[9 empty] | 23.7% | 76.3% |  |  |  | 93.75%
[11 empty] | Remaining | 436831.28
80.23%
REHAB ONLY EXPENSES
[5 empty] | Totals: | 105273.72 | 2395 | 0 | 0 | 107668.72 | 164494 | 3832.28 | 0 | 107668.72 | 543.6333 | #DIV/0! | 627.9667 |  | 84.3333 | 26.96%
Unit | Unit Type | In House or Contractor | Start Date | Completed Date | Move In Date | Actual Total Cost of Items Included on IWO (excl. Appliances) | Actual Total Cost of Appliances | Contracted Labor Cost Per Unit | Rehab Additions Other | Total Cost Expensed to Rehab | Budgeted Rehab Cost Per Unit (Incl. Rehab & Appliances) | Difference | Operations Additions Other | Total Cost of Unit Turn Rehab + Op | Traditional Actual Net Rent (Rent Less Concessions) | Prior Resident Lease Term | Current Resident Actual Net Rent (Rent Less Concessions) | Lease Term | Rent Increase | ROI (over new lease term) | Comments
198 | 1 BR Full | Contractor | 2017-02-07 | 2017-04-02 | 2017-05-04 | 2366.72 |  |  |  | 2366.72 | 3523 | 1156.28 |  | 2366.72 | 505 |  | 580 | 12 | 75 | 38.03%
077 | 2 BR Full | Contractor | 2017-02-22 | 2017-04-27 | 2017-04-28 | 5998 |  |  |  | 5998 | 5054 | -944 |  | 5998 | 658 |  | 753 | 13 | 95 | 20.59% | Costs taken from Yardi
221 | 2 BR Full | Contractor | 2017-02-24 | 2017-04-03 | 2017-09-05 | 5344 |  |  |  | 5344 | 5054 | -290 |  | 5344 | 551 |  | 646 | 12 | 95 | 21.33%
150 | 2 BR Full | Contractor | 2017-02-24 | 2017-05-01 | 2017-06-12 | 4268 |  |  |  | 4268 | 5054 | 786 |  | 4268 | 627 |  | 722 | 12 | 95 | 26.71% | Costs taken from Yardi
141 | 2 BR Full | Contractor | 2017-03-20 | 2017-05-01 | 2017-08-07 | 1977 | 318 |  |  | 2295 | 5054 | 2759 |  | 2295 | 563 |  | 658 | 12 | 95 | 49.67%
002 | 2 BR Full | Contractor | 2017-03-20 | 2017-04-18 | 2018-03-01 | 5960 |  |  |  | 5960 | 5054 | -906 |  | 5960 | 796 |  | 891 | 12 | 95 | 19.13% | Cost taken from Yardi
192 | 2 BR Full | Contractor | 2017-03-20 | 2017-04-18 | 2017-07-21 | 8197 |  |  |  | 8197 | 5054 | -3143 |  | 8197 | 502 |  | 597 | 12 | 95 | 13.91%
050 | 1 BR Full | Contractor | 2017-03-20 | 2017-04-15 | 2017-06-29 | 2531 |  |  |  | 2531 | 3523 | 992 |  | 2531 | 467 |  | 542 | 12 | 75 | 35.56%
153 | 2 BR Full | Contractor | 2017-03-20 | 2017-05-01 | 2017-08-16 | 6553 |  |  |  | 6553 | 5054 | -1499 |  | 6553 | 523 |  | 598 | 12 | 75 | 13.73%
052 | 1 BR Full | Contractor | 2017-05-01 | 2017-05-25 | 2017-05-26 | 3441 | 746 |  |  | 4187 | 3523 | -664 |  | 4187 | 491 |  | 566 | 12 | 75 | 21.5%
047 | 1 BR Full | Contractor | 2017-07-24 | 2017-09-08 | 2018-01-05 | 2333 | 1331 |  |  | 3664 | 3523 | -141 |  | 3664 | 439 |  | 514 | 12 | 75 | 24.56%
051 | 1 BR Full | Contractor | 2017-07-24 | 2017-09-08 | 2017-09-09 | 1832 |  |  |  | 1832 | 3523 | 1691 |  | 1832 | 484 |  | 559 | 12 | 75 | 49.13%
055 | 1 BR Full | Contractor | 2017-07-24 | 2017-09-09 | 2017-09-25 | 3049 |  |  |  | 3049 | 3523 | 474 |  | 3049 | 372 |  | 447 | 12 | 75 | 29.52%
164 | 2 BR Full | Contractor | 2017-07-24 | 2017-08-31 | 2017-09-01 | 3697 |  |  |  | 3697 | 5054 | 1357 |  | 3697 | 496 |  | 591 | 12 | 95 | 30.84%
177 | 2 BR Full | Contractor | 2017-07-24 | 2017-09-01 | 2017-09-29 | 3457 |  |  |  | 3457 | 5054 | 1597 |  | 3457 | 490 |  | 585 | 12 | 95 | 32.98%
178 | 2 BR Full | Contractor | 2017-07-24 | 2017-09-02 | 2017-09-29 | 4451 |  |  |  | 4451 | 5054 | 603 |  | 4451 | 437 |  | 532 | 12 | 95 | 25.61% | Costs taken from Yardi
225 | 1 BR Full | Contractor | 2017-10-09 | 2017-12-15 | 2018-02-19 | 2219 |  |  |  | 2219 | 3523 | 1304 |  | 2219 | 536 |  | 611 | 12 | 75 | 40.56%
075 | 1 BR Full | Contractor | 2017-12-12 | 2017-10-25 | 2018-04-09 | 4918 |  |  |  | 4918 | 3523 | -1395 |  | 4918 | 551 |  | 626 | 11 | 75 | 18.3%
122 | 2 BR Full | Contractor | 2018-02-05 | 2018-02-26 | 2018-02-28 | 5156 |  |  |  | 5156 | 5054 | -102 |  | 5156 | 585 |  | 680 | 13 | 95 | 22.11% | Costs taken from Yardi
172 | 1 BR Full | Contractor | 2018-02-08 | 2018-04-05 | 2018-04-13 | 5087 |  |  |  | 5087 | 3523 | -1564 |  | 5087 | 496 |  | 571 | 13 | 75 | 17.69%
228 | 1 BR Full | Contractor | 2018-03-19 | 2018-04-20 | 2018-04-28 | 5026 |  |  |  | 5026 | 3523 | -1503 |  | 5026 | 524 |  | 599 | 9 | 75 | 17.91%
021 | 1 BR Full | Contractor | 2018-03-19 | 2018-04-27 | 2018-06-15 | 4453 |  |  |  | 4453 | 3523 | -930 |  | 4453 | 589 |  | 664 | 15 | 75 | 20.21%
040 | 2 BR Full | Contractor | 2018-03-21 | 2018-05-17 |  | 1835 |  |  |  | 1835 | 5054 | 3219 |  | 1835
135 | 1 BR Full | Contractor | 2018-04-01 | 2018-04-15 | 2018-05-30 | 2894 |  |  |  | 2894 | 3523 | 629 |  | 2894 | 636 |  | 711 | 13 | 75 | 31.1%
001 | 2 BR Full | Contractor | 2018-04-02 | 2018-04-20 | [6 empty] | 5054
129 | 1 BR Full | Contractor | 2018-04-09 | 2018-05-24 | 2018-05-25 | 2778 |  |  |  | 2778 | 3523 | 745 |  | 2778 | 504 |  | 579 | 13 | 75 | 32.4%
124 | 1 BR Full | Contractor | 2018-04-09 | 2018-06-22 | 2018-06-29 | [5 empty] | 3523 |  |  |  | 494 |  | 569 | 13 | 75
115 | 2 BR Full | Contractor | 2018-04-19 | 2018-07-06 | 2018-07-06 | [5 empty] | 5054 |  |  |  | 620 |  | 715 | 14 | 95
130 | 1 BR Full | Contractor | 2018-05-01 | 2018-05-17 | 2018-06-15 | [5 empty] | 3523 |  |  |  | 504 |  | 579 | 13 | 75
190 | 2 BR Full | Contractor | 2018-05-15 | 2018-06-01 | 2018-06-02 | 5453 |  |  |  | 5453 | 5054 | -399 |  | 5453 | 660 |  | 755 | 13 | 95 | 20.91%
042 | 1 BR Full | Contractor | 2018-07-13 | [7 empty] | 3523
067 | 2 BR Full | Contractor | 2018-05-23 | 2018-06-29 | 2018-06-30 | [5 empty] | 5054 |  |  |  | 625 |  | 720 | 15 | 95
180 | 2 BR Full | Contractor | 2018-05-30 | 2018-06-22 | 2018-06-23 | [5 empty] | 5054 |  |  |  | 584 |  | 679 | 15 | 95
096 | 1 BR Full | Contractor | 2018-06-26 | [7 empty] | 3523
209 | 2 BR Full | Contractor | 2018-06-26 | [7 empty] | 5054
069 | 1 BR Full | Contractor | 2018-07-16 | [7 empty] | 3523
026 | 2 BR Full | Contractor | 2018-07-30 | [7 empty] | 5054
039 | 2 BR Full | Contractor | 2018-09-10 | [7 empty] | 5054
In House
Contractor